Program of the meetings for the implementation of the Agreement on cooperation between the Regional Commonwealth in the field of Communications and the Council of the Interparliamentary Assembly of the Member-States of thee Commonwealth of Independent States.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Names of the Meetings | Executors, Deadlines | Financing | Notes |
| 1. | Creation of the Expert Council of the IPA CIS - RCC | IPA CIS Secretariat, RCC Executive Committee, IPA CIS working bodies, RCC January 2004. | At the Expense of own funds | The composition of the Expert Council includes the heads of the working and executive bodies of the IPA CIS and RCC |
| 2. | Development of the regulatory documents | Temporary Working Group of the Expert Council of the IPA CIS - RCC January 2004. | Expenses will be financed by decision of the Chamber Council of the Federation Council of the Federal Assembly of the Russian Federation | The joint bodies of the RCC and IPA CIS in the implementation of the Agreement are guided by internal legal documents regulating their activities. Additionally the following are being developed: “On the Expert Council of the IPA CIS-RCC”, “On Monitoring, Editing and Amending the Model Legislative Acts of the IPA CIS in the Field of Communications and Informatization”; “On the procedure for choosing organizations of developers of model legislative acts of the IPA CIS in the field of communications and informatizationЭ. |
| 3. | Creation of an integrated database of regulatory legal acts based on the organization of interaction of information systems | RCC Commission on Informatization and Telecommunications, Secretariat of the IPA CIS Council, 2004. | At the Expense of own funds |  |

1

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 4. | Formation of relevant topics and a long-term list of the IPA CIS model legislative acts planned for development | Expert Council of the IPA CIS RCC  March 2004. | At the Expense of own funds |  |
| 5. | Development of indicators for assessing the degree of rapprochement of the national legislation of the IPA CIS member-states for the development of integration processes in the field of communications and informationи | Expert Council of the IPA CIS RCC  2004. | Expenses will be financed by decision of the Chamber Council of the Federation Council of the Federal Assembly of the Russian Federation |  |
| 6. | Definition, coordination of sources and cost of the IPA CIS model legislative acts planned for development | Expert Council of the IPA CIS RCC  2004. |  |  |
| 7. | Organization and holding of tenders for the elections of the organization of developers | Expert Council of the IPA CIS RCC | Expenses will be financed by decision of the Chamber Council of the Federation Council of the Federal Assembly of the Russian Federation |  |

2

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8. | Organization of the development of the Concept of a model information codex of the CIS countries | | Expert Council of the IPA CIS RCC  2004. | | The budget funds of the Verkhovna Rada of Ukraine | |  | |
| 9. | Monitoring of the implementation process of the adopted and recommended for the usage of the IPA CIS model legislative acts and the introduction of the results to the RCC Board of the Communications Administrations Heads and the IPA CIS | | Expert Council of the IPA CIS RCC  2004. | | Expenses will be financed by decision of the Chamber Council of the Federation Council of the Federal Assembly of the Russian Federation | | Monitoring is carried out according to the current model laws “On the principles of regulating information relations in the CIS member-states”; “On transboundary satellite television broadcasting and international satellite information“ On scientific and technical Information ”; “On personal data”; “On electronic digital signature”; “On the international information“; “On telecommunications ” | |
| 10. | Analysis of the harmonization and approximation of the national legislation of the IPA CIS member-states in the field of communications and informatization and its introduction for consideration by the IPA CIS Council and the RCC Board of the Communications Administrations Heads | | Expert Council of the IPA CIS RCC  2004. | | Expenses will be financed by decision of the Chamber Council of the Federation Council of the Federal Assembly of the Russian Federation | |  | |
|  | Names of the Meetings | Executors, deadlines | | Financing | | Notes | |
| 11. | Mutual participation of representatives of IPA CIS and RCC in forums and events aimed at harmonizing national legislations in the field of communications and informatization | IPA CIS Secretariat and the RCC Executive Committee,  Permanently | | At the Expense of own funds | | According to an annually agreed schedule. The IPA CIS Secretariat and the RCC Executive Committee provide relevant official invitations. | |

Annex: Mechanism for the implementation of the Agreement on cooperation between the Regional Commonwealth in the field of Communications and the Council of the Inter-Parliamentary Assembly of the Member-States of the Commonwealth of Independent States  
From the Regional Commonwealth in the field of Communications

General Director of the Executive Committee of the Regional Commonwealth in the field of Communications

N. N. Mukhitdinov

October 2003

From the Council of the Interparliamentary Assembly of the Member-States of the Commonwealth of Independent States

Secretary General of the Council of the Interparliamentary Assembly of the CIS Member-States

M.I. Krotov

October 2003